Date – 2 November 2022
Team ID : PNT2022TMID22832
Project Milestone
IoT Based Smart Crop Protection
System for Agriculture .
03
01
05
1 week
2-3 Week
1 week
02
04
FINAL RELEASE
DESIGNING
INFORMATION
1-2 Week
3 week
Publish of product into
Understanding the
GATHERING
market after alpha and
functional requirements
CODING & TESTING
ASSIGNING
Gather requirements and
beta testing and
of the project and create
basic purpose of the
customer feedback will
Create Python code and
architecture diagram and
Assigning task for each
project.
gathered to improve the
web interface based on
flow chart. Creating outer
person and split the
project.
node red js and connect
layer of UI design.
project work based on the
the IOT device by python
technical and project
scripts and report it in
requirements.
web interface.

---
ACTIVITY LIST
Activity
Activity Title
S.No
Duration
Description
Assign the team members & create the
Understanding
repository in github. Assign the task to each
1.
the Project
1 Week
members and teach how to use and open
Requirement
access the GitHub and IBM Career Education.
Advice student to attend classes of IBM
Starting of
portal create and develop an rough diagram
2.
1 week
Project
based on the project description and gather
information of IOT and IBM project.
Team members & team lead must watch
and learn from classes provided by IBM
4 Week
3.
Attend classes
and Nalaya thiran and must gain access
of MIT Iicense for their project.
Budget & analyse the use of IOT in the project and
Budget and
1 week
discuss with the team for budget prediction to
4.
scope of the
predict the favourability of the customer to buy
project
the product for efficient use of the product among
the environment.